## Sheet1
IDI Risk Management for Supreme Audit Institutions - Quick Reference Guide
Appendix B – Risk register template

## Risk Register
Risk Information | [6 empty] | Risk Rating | [6 empty] | Risk Treatment
Ref# | Risk Identified | Potential Area of Impact | Financial Impact | Cause of Risk | Risk Owner | Risk Status | Risk Consequence | RS Score | Risk Likelihood | RL Score | Criticality Score | Risk Criticality | Faculty of Action | Treatment Approach | Treatment Approach | Treatment Approach | Migitation Action(s) | Expected Benefit | Action Owner | Resource Required | Completion Date | Constraints | Performance Measure(s)
R1 | Ever increasing scope of audit not matched by an increase in resource | Audit & reputation |  | Lack of resource and lack of understanding of the work done by political authorities | Auditor General | Open | Major​ | 4 | Likely ​ | 4 | 16 | High Criticality | High | Retain | Change consequence | Change likelihood | Review SAI structure to increase staff establishment to match the widening scope - Widen the use of automated checks in financial audits - Lobby for increases in the SAI budget to cater for increase in scope | Leaner use of audit resource - Enhanced capacity to handle more audits | SAI management team - Deputy AG for audit | Internal reallocation | 2024-12-31 |  | Percentage of audit coverage stays at same level despite increase in scope
R2 | Lack of proper audit IT tool | Audits |  | Audit software outdated and product to be discontinued by the provider | Head of IT | Open | Major​ | 4 | Near to Certain​ | 5 | 20 | Extreme Criticality | High | Remove risk source |  |  | Procurement of a new audit software & Training of auditors | Maintain and enhance audit capability | Head of IT & Head of HR | 2M NOK | 2023-06-30 | Procurement rules creating delays | New software procured and deployed by 30 June 2023 & number of auditors successfully trained (certificates to be delivered by trainers after test)
R3 | Declining SAI reputation and growing negative perception of the office |  |  | Allegations of unethical conduct among SAI staff - Limited adherence to office core values by staff | Deputy AG for Administration | Observe | Moderate​ | 3 | Moderate ​ | 3 | 9 | Moderate Criticality | Significant | Change likelihood | Change consequence |  | Implement structures to stregthen integrity - Investigate and conclude all corruption allegations and take punitive action - Instill and monitor a SAI culture that embraces and enforces integrity and professionalism |  | Head of HR |  | 2023-12-31 |  | Percentage of misconduct cases that are formally investigates
R4 | Expectation gaps among key stakeholders | SAI strategy & audits |  | Limited understanding of the mandate and role of the SAI in the accountability cycle | Auditor General | Observe | Minor​ | 2 | Unlikely​ | 2 | 4 | Low Criticality ​ | Significant | Retain | Change likelihood |  | Publish the strategy and the annual audit plan | Better understanding leading to better acceptance and more aligned expectations | SAI Secretary General - Deputy AG for audit | 50k NOK | 2023-05-30 |  | Number of documents printed and distributed - Number of views of the website
R-1 | Payroll non-confirmity | HR | >5M NOK (legal fees) | Lack of updated information sent to the Treasury | Deputy AG for Administration | Closed | Minor​ | 2 | Insignificant​ | 1 | 2 | Low Criticality ​ | High | Remove risk source |  |  | Update staff files and send updated information to Treasury in charge of payroll | Staff paid according to their current position and seniority | Head of HR | 0.2 HR FTE (internal) | 31/01/2023 (then monthly) | Recurring task | 100% accurate payroll
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A
[8 empty] | #N/A |  | #N/A | #N/A

## Sheet5 (hidden)
Impact ​ | Impact Score | likelyhood | Likelyhood score |  | Risk Level
Catastrophic​ | 5 | Near to Certain​ | 5 | 1 | Low Criticality ​
Major​ | 4 | Likely ​ | 4 | 2 | Low Criticality ​
Moderate​ | 3 | Moderate ​ | 3 | 3 | Low Criticality ​
Minor​ | 2 | Unlikely​ | 2 | 4 | Low Criticality ​
Insignificant​ | 1 | Insignificant​ | 1 | 5 | Moderate Criticality
|  |  |  | 6 | Moderate Criticality
|  |  |  | 8 | Moderate Criticality
|  |  |  | 9 | Moderate Criticality
|  |  |  | 10 | Moderate Criticality
|  |  |  | 12 | High Criticality
|  |  |  | 15 | High Criticality
|  |  |  | 16 | High Criticality
|  |  |  | 20 | Extreme Criticality
|  |  |  | 25 | Extreme Criticality
Risk treament options |  |  | Faculty of action
Avoid |  |  | High
Take or increase to pursue opportunity |  |  | Significant
Remove risk source |  |  | Limited
Change likelihood |  |  | Null
Change consequence
Share
Retain
Risk status
Open
Closed
Observe

## Risk Matrix
Risk Rating (Likelihood x Impact = Criticality) ​
1-4 | Low Criticality ​ | Rating 1​ | Code Green ​
5-10 | Moderately Critical ​ | Rating 2​ | Code Yellow ​
12-16 | Highly Critical ​ | Rating 3​ | Code Orange
20-25 | Extreme Criticality | Rating 4 | Code Red​
Impact ​ | Likelihood ​
| Insignificant​ | Unlikely​ | Moderate ​ | Likely ​ | Near to Certain​
Catastrophic​ | 5​ | 10​ | 15​ | 20​ | 25​
Major​ | 4​ | 8​ | 12​ | 16​ | 20​
Moderate​ | 3​ | 6​ | 9​ | 12​ | 15​
Minor​ | 2​ | 4​ | 6​ | 8​ | 10​
Insignificant​ | 1​ | 2​ | 3​ | 4​ | 5​

## Action Tracker
Completion Date | (All)
Column Labels
| (blank) | (blank) Total | Grand Total
Row Labels | (blank)
(blank)
Grand Total